## Andy
Name | Date | Hours | Task | Description
Andy Adelman | 2026-10-17 | 3.25 | Report development and planning | Organized the final report structure. Drafted and refined requirements, Meal Club, physical implementation, requirements review, and ethics sections.
Andy Adelman | 2026-10-17 | 2.5 | SQL script refinement and testing | Reformatted the database build script into Version 1.4. Removed duplicate query commentary. Executed the script and resolved DBeaver display issues.
Andy Adelman | 2026-10-17 | 3 | Query analysis and report evidence | Ran the ten business queries. Exported results and screenshots. Drafted the Sample Queries section with business questions, output, interpretation, and actions.
Andy Adelman | 2026-10-17 | 0.75 | Version control and project assets | Initialized and organized the Git repository. Added query-output assets, screenshots, and report updates in separate commits.
Andy Adelman | 2026-10-02 | 1 | Reviewed conceptual ERD | Reviewed entity coverage, relationships, cardinality, and optionality.
Andy Adelman | 2026-10-09 | 1.5 | Reviewed relational ERD | Reviewed primary and foreign keys, composite constraints, data types, and normalization.
Andy Adelman | multiple | 1.5 | Team project meetings and coordination | Three 30-minute meetings
Andy Adelman | multiple | 1 | Set up shared project workspace and file-sharing structure | Created collaboration and version-control workspace
Andy Adelman | 2026-09-25 | 2.5 | Requirements planning and project setup | Organized requirements, scope, workstreams, report structure, and task plan
Andy Adelman | 2026-10-19 | 1.75 | Organization overview and references | Finalized the Organization Overview. Added and reviewed figure captions, superscript citations, screenshots, and the related reference entries.
Andy Adelman | 2026-10-19 | 0.5 | Scope, requirements, and appendices | Finalized the scope and assumptions narrative. Completed Appendix A and Appendix B. Added the requirements-register cross-reference to the prioritized requirements section.
Andy Adelman | 2026-10-27 | 2.25 | Conceptual-model finalization | Rebuilt and exported the final conceptual-model views in Lucidchart; revised the conceptual-model narrative, comparison material, figures, and Appendix C
Andy Adelman | 2026-10-27 | 2 |  | Audited the report against project requirements; created the final requirements-review register and narrative; updated appendices, contribution records, report assets, and Git staging

## Eddie
Name | Date | Hours | Task | Description
Eduardo Rodriguez | Not provided | 2 | Requirements and model review | Scope and relationships
Eduardo Rodriguez | Not provided | 3 | Schema and sample-data review | AI-assisted SQL draft
Eduardo Rodriguez | Not provided | 2 | Business-query and validation review | Outputs and data quality
Eduardo Rodriguez | Not provided | 2 | Review findings and design decisions | Open issues and rationale
Eduardo Rodriguez | Not provided | 1 | Documentation and team handoff | AI log and supporting files

## Rashy
Name | Date | Hours | Task | Description
Rasheedat Emiola | 10/2–10/4/2026 | 4 | Relational model development | Drafted relational model: attributes, primary/foreign keys, junction tables; built tables in Lucid; applied group feedback (pickup vs delivery, loyalty cardinality, benefit events)
Rasheedat Emiola | 2026-10-04 | 1 | Relational model review submission | Added lengths/NOT NULL per teammate feedback; reviewed conceptual and relational models for the review submission; helped prepare the submission PDF
Rasheedat Emiola | 2026-10-07 | 1 | Instructor feedback review | Read professor feedback; worked out what it meant for the relational model
Rasheedat Emiola | 10/13–10/14/2026 | 1 | Relational-model revision | Edited relational model in Lucid: removed data types and relationship names, fixed typo, corrected composite unique key; exported PDF; uploaded to group Drive
Rasheedat Emiola | 10/16–10/19/2026 | 1 | Relational-model documentation | Prepared explanation of the relational model; prepared documentation for the report

## Kithrika
Name | Date | Hours | Task | Description
Krithika Rees | 2026-09-27 | 1 | V0 - Starting design | Prepared or reviewed original conceptual and relational drafts (V0).
Krithika Rees | 2026-10-08 | 1 | V1 - Conceptual readability | Used Lucidchart to revise conceptual presentation and attributes (V1); reviewed exported result.
Krithika Rees | 2026-10-13 | 1 | V2 - Relational mapping | Generated/reviewed relational mapping and associative tables (V2).
Krithika Rees | 2026-10-18 | 1 | Intermediate normalization review | Reviewed 3NF concerns and logical structure; compared intermediate review diagram.
Krithika Rees | 2026-10-19 | 1 | V3 - Corrected final logical diagram | Rebuilt/reviewed final Crow’s Foot logical ERD with visible PK/FK columns (V3); exported PDF.
Krithika Rees | 2026-10-23 | 3 | Model-evolution documentation | Prepared model-evolution documentation and normalization analysis.

## Daniel
* At the time of this writing, Daniel Steffen has not submitted any hours.